## Khoá Thanh Toán
DỰ ÁN POWER BANKING - KHỐ THANH TOÁN
Cập nhật: 07/04/2026 ¦ Tổng Chi Phí: 386,000,000 VND ¦ Thời gian: ~250 ngày
Đợt | Tên Gọi | Thời Điểm (Tuần) | % Chi Phí | Số Tiền (VND) | Tích Lũy (VND) | Điều Kiện Thanh Toán | Ghi Chú | Trạng Thái
1 | Hợp đồng & Kick-off | Ngay | 20% | 77200000 | 77200000 | Ký hợp đồng, kick-off meeting | Hardware design bắt đầu | Chờ ký
2 | Hardware + Backend v1 | Tuần 8 | 20% | 77200000 | 154400000 | Hardware prototype hoàn thành, Backend APIs v1 ready | Tested & deployed staging | Chờ xác nhận
3 | Frontend hoàn thành | Tuần 14 | 20% | 77200000 | 231600000 | Frontend Owner + User hoàn thành, QA riêng pass | Both frontends integrated | Chờ xác nhận
4 | QA & UAT | Tuần 19 | 20% | 77200000 | 308800000 | Full QA pass, UAT completed, production ready | Performance optimized | Chờ xác nhận
5 | Go-live & Support | Tuần 20+ | 20% | 77200000 | 386000000 | Production deployment, 3 tháng support | 24/7 monitoring, warranty | Chờ xác nhận

## Milestone-1
MILESTONE 1 - HARDWARE + BACKEND V1 (ĐỢT 2)
Thời điểm: Tuần 8 ¦ Chi phí: 77,200,000 VND ¦ 20% tổng dự án
HARDWARE (Kiểm duyệt)
☐ PCB design hoàn thành, đã ordered
☐ Firmware ESP32 cơ bản hoàn thành
☐ ✓ 4G connection & MQTT pub/sub working
☐ ✓ 8 GPIO relay control working
☐ Device prototype điều khiển từ server
☐ Hardware burn-in test started (24h+)
Deliverables: Hardware prototype (1-2 units), Test reports
BACKEND (Kiểm duyệt)
☐ Database schema deployed (PostgreSQL)
☐ User Management API (register, login, JWT) ✓
☐ Device Management API (list, create, update) ✓
☐ Device Status API (real-time via MQTT) ✓
☐ Basic Transaction API ✓
☐ MQTT Broker configured & running ✓
☐ API Documentation (Swagger) ✓
☐ Unit tests pass (>70% coverage) ✓
☐ Staging environment deployed & accessible ✓
Deliverables: Postman collection, Database backup, Deployment guide, Test reports

## Milestone-2
MILESTONE 2 - FRONTEND HOÀN THÀNH (ĐỢT 3)
Thời điểm: Tuần 14 ¦ Chi phí: 77,200,000 VND ¦ 20% tổng dự án
FRONTEND OWNER - CHỦ DEVICE
☐ Login/Register/Profile ✓
☐ Device list & control (on/off khay) ✓
☐ Set charging time per slot ✓
☐ Transaction history & analytics ✓
☐ Revenue reports & export ✓
☐ Notifications (email/SMS) ✓
☐ Mobile responsive working ✓
☐ Deployed on staging ✓
FRONTEND USER - NGƯỜI DÙNG
☐ Registration & KYC verification ✓
☐ Device search (map + filters) ✓
☐ Rental flow (select → checkout) ✓
☐ Momo payment integration ✓
☐ QR code scanner for check-in ✓
☐ Timer & time tracking ✓
☐ Transaction history ✓
☐ Push notifications ✓
☐ Deployed on staging ✓
QA - TESTING
☐ Functional testing (all features) ✓
☐ Edge cases & error handling ✓
☐ Performance baseline established ✓
☐ Security scan done ✓
☐ QA report pass rate >95% ✓

## Milestone-3
MILESTONE 3 - QA + UAT + OPTIMIZATION (ĐỢT 4)
Thời điểm: Tuần 19 ¦ Chi phí: 77,200,000 VND ¦ 20% tổng dự án
FULL SYSTEM TESTING
☐ Integration testing (Hardware + Backend + Frontend)
☐ Load testing (1000+ concurrent users)
☐ All critical bugs fixed
☐ Performance optimization completed
☐ Security audit passed
USER ACCEPTANCE TESTING (UAT)
☐ UAT with sample users (Min 50 test cases)
☐ UAT test pass rate ≥ 95%
☐ User feedback addressed
☐ Production checklist completed
PRODUCTION READINESS
☐ Database auto-backup configured
☐ Monitoring & alerting setup
☐ Logging system ready
☐ Disaster recovery plan documented
☐ Scaling plan documented
☐ SLA defined & communicated

## Timeline
TIMELINE & THANH TOÁN
Tuần | Công Việc Chính | Điểm Checkup | Thanh Toán | Progress
W1-2 | Design + Kick-off | Planning done | ĐỢT 1: 90.4M | 0%
W3-6 | Hardware + Backend | 50% done | - | 25%
W7-8 | Hardware Ready | Milestone 1 ✓ | ĐỢT 2: 90.4M | 40%
W9-12 | Frontend Dev | 70% done | - | 55%
W13-14 | Frontend QA | Milestone 2 ✓ | ĐỢT 3: 90.4M | 65%
W15-18 | Full Testing + UAT | 90% done | - | 80%
W19 | Go-live Prep | Milestone 3 ✓ | ĐỢT 4: 90.4M | 90%
W20-24 | Production + Support | Live ✓ | ĐỢT 5: 90.4M | 100%